## Product Backlog
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed? | Notes
Create Unity project | 15 | 1 | 5 | 1 | Yes
Download design document Template | 15 | 1 | 5 | 1 | Yes
Create a Player with physics | 15 | 2 | 60 | 1 | Yes |  | Estimated time taken to complete project: | 1410 | Mins
Make a ground in which the player can jump on | 15 | 1 | 15 | 1 | Yes |  | Actual time taken to compelte project: | 1664 | Mins
Create jumping and movement W/A/S/D + Space | 30 | 3 | 145 | 4 | Yes
Create a death sequence | 30 | 3 | 30 | 4 | Yes |  | Estimated effort to complete project: | 80
Create a mechanic | 30 | 4 | 60 | 4 | Yes |  | Actual effort to complete project: | 91
Make a map | 60 | 3 |  | 3 | In Progress
Add a dash | 30 | 4 |  |  | Scrapped | Dash mechanic did not feel good for the platformer after I made it
Create a sidescroll style camera | 30 | 3 | 60 | 5 | Yes
make a test level | 15 | 1 | 9 | 1 | Yes
make an audio visualiser | 60 | 5 |  | 5 | Moved to Next Sprint | This was quite hard to do so I left it for another week to finish
find a game to reference for the levels | 15 | 1 | 10 | 1 | Yes
post processing effects | 15 | 2 | 30 | 3 | Yes
moving traps/spikes | 30 | 3 | 60 | 4 | Yes
teleporter | 60 | 3 | 60 | 4 | Yes
exit door | 15 | 2 | 30 | 2 | Yes
find a music genre to suit the game | 15 | 1 | 15 | 1 | Yes
make an audio visualiser | 60 | 5 | 120 | 5 | Yes
make 3 playable levels | 120 | 3 | 120 | 3 | Yes
pause menu | 120 | 4 |  | 5 | Moved to Next Sprint | Gave up on this for current sprint as it took way too long for some reason I kept running into issues with the buttons not working due to my mouse image overlapping
death counter | 15 | 2 | 30 | 2 | Yes
level reset/trap reset on death | 120 | 3 | 90 | 4 | Yes
trigger zones for more complex traps | 60 | 3 | 60 | 4 | Yes
movable platforms | 30 | 2 | 30 | 3 | Yes
camera adjustments | 15 | 2 | 30 | 2 | Yes
pause menu | 60 | 4 | 90 | 5 | Yes
main menu | 60 | 2 | 90 | 3 | Yes
more death taunts | 15 | 2 | 30 | 2 | Yes
2 more levels | 120 | 2 | 180 | 3 | Yes
Hard mode |  |  |  |  | Scrapped | too complex
skins |  |  |  |  | Scrapped | too complex
settings | 120 | 3 | 200 | 5 | Yes | This was hard as I have never doone settings before but I got there
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort
Starting Values | 1410 | 1664 | 80 | 91
Create Unity project | 1395 | 1659 | 79 | 90
Download design document Template | 1380 | 1654 | 78 | 89
Create a Player with physics | 1365 | 1594 | 76 | 88
Make a ground in which the player can jump on | 1350 | 1579 | 75 | 87
Create jumping and movement W/A/S/D + Space | 1320 | 1434 | 72 | 83
Create a death sequence | 1290 | 1404 | 69 | 79
Create a mechanic | 1260 | 1344 | 65 | 75
Make a map | 1200 | 1344 | 62 | 72
Add a dash | 1170 | 1344 | 58 | 72
Create a sidescroll style camera | 1140 | 1284 | 55 | 67
make a test level | 1125 | 1275 | 54 | 66
make an audio visualiser | 1065 | 1275 | 49 | 61
find a game to reference for the levels | 1050 | 1265 | 48 | 60
post processing effects | 1035 | 1235 | 46 | 57
moving traps/spikes | 1005 | 1175 | 43 | 53
teleporter | 945 | 1115 | 40 | 49
exit door | 930 | 1085 | 38 | 47
find a music genre to suit the game | 915 | 1070 | 37 | 46
make an audio visualiser | 855 | 950 | 32 | 41
make 3 playable levels | 735 | 830 | 29 | 38
pause menu | 615 | 830 | 25 | 33
death counter | 600 | 800 | 23 | 31
level reset/trap reset on death | 480 | 710 | 20 | 27
trigger zones for more complex traps | 420 | 650 | 17 | 23
movable platforms | 390 | 620 | 15 | 20
camera adjustments | 375 | 590 | 13 | 18
pause menu | 315 | 500 | 9 | 13
main menu | 255 | 410 | 7 | 10
more death taunts | 240 | 380 | 5 | 8
2 more levels | 120 | 200 | 3 | 5
Hard mode | 120 | 200 | 3 | 5
skins | 120 | 200 | 3 | 5
settings | 0 | 0 | 0 | 0
Key:
Expected Completion time is in blocks of 15 minutes, e.g 15, 30, 45 ...120 - this could be changed to suit your project, but time blocks work well here!
Effort Values are between 1-5
1 being easy
5 being very difficult
Again, this could be changed here, but this set of numbers works well!

## Sprint 1
Sprint 1
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
Create Unity project | 15 | 1 | 5 | 1 | Yes
Download design document Template | 15 | 1 | 5 | 1 | Yes
Create a Player with physics | 15 | 2 | 60 | 1 | Yes
Make a ground in which the player can jump on | 15 | 1 | 15 | 1 | Yes
Create jumping and movement W/A/S/D + Space | 30 | 3 | 145 | 4 | Yes
Create a death sequence | 30 | 3 | 30 | 4 | Yes
Create a mechanic | 30 | 4 | 60 | 4 | Yes
Make a map | 60 | 3 |  | 3 | In Progress
Add a dash | 30 | 4 |  |  | Scrapped
Create a sidescroll style camera | 30 | 3 | 60 | 5 | Yes
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 270
Starting Values | 270 | 380 | 25 | 24 |  | Actual time taken to compelte sprint: | 380
Create Unity project | 255 | 375 | 24 | 23
Download design document Template | 240 | 370 | 23 | 22 |  | Estimated effort to complete sprint: | 25
Create a Player with physics | 225 | 310 | 21 | 21 |  | Actual effort to complete sprint: | 24
Make a ground in which the player can jump on | 210 | 295 | 20 | 20
Create jumping and movement W/A/S/D + Space | 180 | 150 | 17 | 16
Create a death sequence | 150 | 120 | 14 | 12
Create a mechanic | 120 | 60 | 10 | 8
Make a map | 60 | 60 | 7 | 5
Add a dash | 30 | 60 | 3 | 5
Create a sidescroll style camera | 0 | 0 | 0 | 0
Here you can put your actual sprint tasks, as you complete tasks, remember to update your full product backlog!
Sprint Analysis:
After you have finished each sprint, you can work out how productive you actually were!
Turn this empty chart into a Burndown Chart
You could put any other analysis here!
Why not also reflect a little? Write overall how it went!

## Sprint 2
Sprint 2
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
make a test level | 15 | 1 | 9 | 1 | Yes
make an audio visualiser | 60 | 5 |  | 5 | Moved to Next Sprint
find a game to reference for the levels | 15 | 1 | 10 | 1 | Yes
post processing effects | 15 | 2 | 30 | 3 | Yes
moving traps/spikes | 30 | 3 | 60 | 4 | Yes
teleporter | 60 | 3 | 60 | 4 | Yes
exit door | 15 | 2 | 30 | 2 | Yes
find a music genre to suit the game | 15 | 1 | 15 | 1 | Yes
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 225
Starting Values | 225 | 214 | 18 | 21 |  | Actual time taken to compelte sprint: | 214
make a test level | 210 | 205 | 17 | 20
make an audio visualiser | 150 | 205 | 12 | 15 |  | Estimated effort to complete sprint: | 18
find a game to reference for the levels | 135 | 195 | 11 | 14 |  | Actual effort to complete sprint: | 21
post processing effects | 120 | 165 | 9 | 11
moving traps/spikes | 90 | 105 | 6 | 7
teleporter | 30 | 45 | 3 | 3
exit door | 15 | 15 | 1 | 1
find a music genre to suit the game | 0 | 0 | 0 | 0
Here you can put your actual sprint tasks, as you complete tasks, remember to update your full product backlog!
Sprint Analysis:
After you have finished each sprint, you can work out how productive you actually were!
Turn this empty chart into a Burndown Chart
You could put any other analysis here!
Why not also reflect a little? Write overall how it went!

## Sprint 3
Sprint 3
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
make an audio visualiser | 60 | 5 | 120 | 5 | Yes
make 3 playable levels | 120 | 3 | 120 | 3 | Yes
pause menu | 120 | 4 |  | 5 | Moved to Next Sprint
death counter | 15 | 2 | 30 | 2 | Yes
level reset/trap reset on death | 120 | 3 | 90 | 4 | Yes
trigger zones for more complex traps | 60 | 3 | 60 | 4 | Yes
movable platforms | 30 | 2 | 30 | 3 | Yes
camera adjustments | 15 | 2 | 30 | 2 | Yes
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 540
Starting Values | 540 | 480 | 24 | 28 |  | Actual time taken to compelte sprint: | 480
make an audio visualiser | 480 | 360 | 19 | 23
make 3 playable levels | 360 | 240 | 16 | 20 |  | Estimated effort to complete sprint: | 24
pause menu | 240 | 240 | 12 | 15 |  | Actual effort to complete sprint: | 28
death counter | 225 | 210 | 10 | 13
level reset/trap reset on death | 105 | 120 | 7 | 9
trigger zones for more complex traps | 45 | 60 | 4 | 5
movable platforms | 15 | 30 | 2 | 2
camera adjustments | 0 | 0 | 0 | 0
Here you can put your actual sprint tasks, as you complete tasks, remember to update your full product backlog!
Sprint Analysis:
After you have finished each sprint, you can work out how productive you actually were!
Turn this empty chart into a Burndown Chart
You could put any other analysis here!
Why not also reflect a little? Write overall how it went!

## Sprint 4
Sprint 4
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
pause menu | 60 | 4 | 90 | 5 | Yes
main menu | 60 | 2 | 90 | 3 | Yes
more death taunts | 15 | 2 | 30 | 2 | Yes
2 more levels | 120 | 2 | 180 | 3 | Yes
Hard mode |  |  |  |  | Scrapped
skins |  |  |  |  | Scrapped
settings | 120 | 3 | 200 | 5 | Yes
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 375
Starting Values | 375 | 590 | 13 | 18 |  | Actual time taken to compelte sprint: | 590
pause menu | 315 | 500 | 9 | 13
main menu | 255 | 410 | 7 | 10 |  | Estimated effort to complete sprint: | 13
more death taunts | 240 | 380 | 5 | 8 |  | Actual effort to complete sprint: | 18
2 more levels | 120 | 200 | 3 | 5
Hard mode | 120 | 200 | 3 | 5
skins | 120 | 200 | 3 | 5
settings | 0 | 0 | 0 | 0
Here you can put your actual sprint tasks, as you complete tasks, remember to update your full product backlog!
Sprint Analysis:
After you have finished each sprint, you can work out how productive you actually were!
Turn this empty chart into a Burndown Chart
You could put any other analysis here!
Why not also reflect a little? Write overall how it went!