## Product Backlog
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed? | Notes
Create Unity project | 15 | 1 | 5 | 1 | Yes | Done!
Download design document Template | 15 | 1 | 5 | 1 | Yes | Done!
Create a Player with physics | 15 | 2 | 60 | 2 | Yes | Done! | Estimated time taken to complete project: | 5285 | Mins
Rolling orb movement | 15 | 1 | 60 | 3 | Yes | Done! | Actual time taken to compelte project: | 5925 | Mins
Camera follow system | 30 | 3 | 145 | 4 | Yes | Done!
Create a death sequence | 30 | 3 | 120 | 4 | Yes | Done! | Estimated effort to complete project: | 82
Create a mechanic | 30 | 4 | 180 | 5 | Yes | Done! | Actual effort to complete project: | 72
Procedural dune generation | 500 | 3 |  |  | Moved to Next Sprint | was still leanring how to do it so I moved it to next week
Test moving floor system | 400 | 3 |  |  | Scrapped | this did not work as it was to complex for me to figure out
Procedural dune generation | 300 | 4 | 1500 | 5 | Yes | Done!
Score system | 120 | 3 | 200 | 3 | Yes | Done!
Infinite terrain generation | 800 | 5 | 1000 | 5 | In Progress | was able to make it work but never fixed the bugs for it
post processing effects | 15 | 2 | 30 | 3 | Yes | Done!
UI Setup | 60 | 2 | 120 | 3 | Yes | Done!
Fix tessellation errors | 60 | 3 |  |  | Scrapped | Done!
Treadmill idea | 500 | 5 |  |  | Scrapped | Done!
Infinite terrain generation | 500 | 5 | 800 | 5 | Yes | tried to get rid of bugs and made it better but there was still some so I thought it was not worth the time to fix
Main Menu | 120 | 3 | 120 | 3 | Yes | Done!
pause menu | 120 | 4 |  | 5 | Moved to Next Sprint | was burnt out
pause menu | 60 | 4 | 120 | 5 | Yes | Done!
story messages narration | 400 | 2 | 320 | 3 | Yes | Done!
lots of balancing | 500 | 2 | 320 | 2 | Yes | Done!
UI Bug fixes | 120 | 2 | 200 | 3 | Yes | Done!
Music Transitions | 60 | 1 | 120 | 3 | Yes | Done!
playtesting | 200 | 11 | 200 | 1 | Yes | Done!
documentation | 300 | 3 | 300 | 3 | Yes | Done!
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort
Starting Values | 5285 | 5925 | 82 | 72
Create Unity project | 5270 | 5920 | 81 | 71
Download design document Template | 5255 | 5915 | 80 | 70
Create a Player with physics | 5240 | 5855 | 78 | 68
Rolling orb movement | 5225 | 5795 | 77 | 65
Camera follow system | 5195 | 5650 | 74 | 61
Create a death sequence | 5165 | 5530 | 71 | 57
Create a mechanic | 5135 | 5350 | 67 | 52
Procedural dune generation | 4635 | 5350 | 64 | 52
Test moving floor system | 4235 | 5350 | 61 | 52
Procedural dune generation | 3935 | 3850 | 57 | 47
Score system | 3815 | 3650 | 54 | 44
Infinite terrain generation | 3015 | 2650 | 49 | 39
post processing effects | 3000 | 2620 | 47 | 36
UI Setup | 2940 | 2500 | 45 | 33
Fix tessellation errors | 2880 | 2500 | 42 | 33
Treadmill idea | 2380 | 2500 | 37 | 33
Infinite terrain generation | 1880 | 1700 | 32 | 28
Main Menu | 1760 | 1580 | 29 | 25
pause menu | 1640 | 1580 | 25 | 20
pause menu | 1580 | 1460 | 21 | 15
story messages narration | 1180 | 1140 | 19 | 12
lots of balancing | 680 | 820 | 17 | 10
UI Bug fixes | 560 | 620 | 15 | 7
Music Transitions | 500 | 500 | 14 | 4
playtesting | 300 | 300 | 3 | 3
documentation | 0 | 0 | 0 | 0
Overall I think the project was successful because I managed to create a fully playable prototype with procedural terrain generation, physics based movement, score systems, UI systems, dynamic music and story narration. One of the biggest strengths of the project is the scene created through the combo of visuals, audio and movement. The procedural dunes and momentum based gameplay helped the game feel fast paced and unique.
The biggest challenge during development was managing scope. I attempted several advanced systems including moving floor mechanics, treadmill terrain generation, procedural dunes, dynamic narration and music blending. Some ideas had to be scrapped because they became too technically complicated or would have taken too much development time. I also experienced burnout during Sprint 3 because I completed such a large amount of work during the first half of the project.
If I continued development further, I would focus mainly on expanding the story elements and improving environmental variety rather than adding more to the gameplay.

## Sprint 1
Sprint 1
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
Create Unity project | 15 | 1 | 5 | 1 | Yes
Download design document Template | 15 | 1 | 5 | 1 | Yes
Create a Player with physics | 15 | 2 | 60 | 2 | Yes
Rolling orb movement | 15 | 1 | 60 | 3 | Yes
Camera follow system | 30 | 3 | 145 | 4 | Yes
Create a death sequence | 30 | 3 | 120 | 4 | Yes
Create a mechanic | 30 | 4 | 180 | 5 | Yes
Procedural dune generation | 500 | 3 |  |  | Moved to Next Sprint
Test moving floor system | 400 | 3 |  |  | Scrapped
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 1050
Starting Values | 1050 | 575 | 21 | 20 |  | Actual time taken to compelte sprint: | 575
Create Unity project | 1035 | 570 | 20 | 19
Download design document Template | 1020 | 565 | 19 | 18 |  | Estimated effort to complete sprint: | 21
Create a Player with physics | 1005 | 505 | 17 | 16 |  | Actual effort to complete sprint: | 20
Rolling orb movement | 990 | 445 | 16 | 13
Camera follow system | 960 | 300 | 13 | 9
Create a death sequence | 930 | 180 | 10 | 5
Create a mechanic | 900 | 0 | 6 | 0
Procedural dune generation | 400 | 0 | 3 | 0
Sprint 1 was the most productive part of the project because I managed to create most of the core gameplay systems very early. I started by setting up the Unity project and downloading the documentation templates so I could keep organised from the beginning. After that I focused mainly on the player movement and physics systems because the movement is the main mechanic of the game. Creating the rolling orb movement took a lot of experimentation with Rigidbody2D forces and momentum because I wanted the movement to feel smooth and satisfying rather than stiff or unrealistic. I also made the camera follow system and death sequence which helped the prototype start to feel like an actual game instead of just a test scene.
During this sprint I also started thinking about how I would handle the terrain generation. My original idea was to create a treadmill style system where chunks of terrain would recycle around the player instead of constantly spawning and deleting objects. I tested a moving floor system as well where the environment would move instead of the player, but this became too complicated and difficult to combine with the physics based movement. Because of this I decided to scrap the moving floor idea and move procedural dune generation into the next sprint instead. Overall Sprint 1 went very well and gave me a strong foundation for the rest of the project, although I probably over-scoped slightly by attempting too many advanced systems early on.

## Sprint 2
Sprint 2
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
Procedural dune generation | 300 | 4 | 1500 | 5 | Yes
Score system | 120 | 3 | 200 | 3 | Yes
Infinite terrain generation | 800 | 5 | 1000 | 5 | In Progress
post processing effects | 15 | 2 | 30 | 3 | Yes
UI Setup | 60 | 2 | 120 | 3 | Yes
Fix tessellation errors | 60 | 3 |  |  | Scrapped
Treadmill idea | 500 | 5 |  |  | Scrapped
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 1855
Starting Values | 1855 | 2850 | 24 | 19 |  | Actual time taken to compelte sprint: | 2850
Procedural dune generation | 1555 | 1350 | 20 | 14
Score system | 1435 | 1150 | 17 | 11 |  | Estimated effort to complete sprint: | 24
Infinite terrain generation | 635 | 150 | 12 | 6 |  | Actual effort to complete sprint: | 19
post processing effects | 620 | 120 | 10 | 3
UI Setup | 560 | 0 | 8 | 0
Fix tessellation errors | 500 | 0 | 5 | 0
Treadmill idea | 0 | 0 | 0 | 0
Sprint 2 i focused a lot on procedural generation and gameplay. This was one of the hardest parts of the project because generating smooth dunes dynamically caused many issues with collisions, tessellation errors, and terrain shapes breaking unexpectedly. After researching procedural generation techniques online and experimenting with Perlin noise systems, I eventually managed to create working procedural dunes that generated infinitely as the player moved forward.
I also added the score system and infinite terrain generation during this sprint. The score system worked together with the player speed and multiplier systems to reward skilled movement and maintaining momentum. Infinite terrain generation was partially completed during this sprint but still needed optimisation and polishing. One of the main problems I encountered was Unity SpriteShape tessellation errors was caused by spline points overlapping too close. I attempted to fix this for a long time but eventually accepted the occasional warning because the dunes themselves still rendered correctly.
I also added post processing effects and UI elements to improve the atmosphere of the game. The treadmill terrain idea from Sprint 1 was scrapped during this stage because procedural generation ended up being a more effective solution. This sprint was difficult technically but it was also the point where the project started feeling good and interesting.

## Sprint 3
Sprint 3
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
Infinite terrain generation | 500 | 5 | 800 | 5 | Yes
Main Menu | 120 | 3 | 120 | 3 | Yes
pause menu | 120 | 4 |  | 5 | Moved to Next Sprint
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 740
Starting Values | 740 | 920 | 12 | 13 |  | Actual time taken to compelte sprint: | 920
Infinite terrain generation | 240 | 120 | 7 | 8
Main Menu | 120 | 0 | 4 | 5 |  | Estimated effort to complete sprint: | 12
pause menu | 0 | 0 | 0 | 0 |  | Actual effort to complete sprint: | 13
Sprint 3 was the least productive sprint from the burnout from the amount of work i completed earlier in development. Most of the main systems had already been created by this point, so I mainly focused on finishing the infinite terrain generation system and creating the main menu. Although I did complete the terrain system successfully, progress overall was much slower compared to previous sprints.
The pause menu was started during this sprint but had to be moved into Sprint 4 because I had UI interaction issues with buttons not responding correctly while the game was paused so i got frustrated and put it for next week. I also spent time testing gameplay balance and fixing smaller issues that appeared after longer play sessions. Even though this sprint was less productive, I still managed to complete important polishing tasks and continue improving overall.

## Sprint 4
Sprint 4
Task | Expected Completion Time | Expected Effort Value | Actual Completion Time | Actual Effort Value | Completed?
pause menu | 60 | 4 | 120 | 5 | Yes
story messages narration | 400 | 2 | 320 | 3 | Yes
lots of balancing | 500 | 2 | 320 | 2 | Yes
UI Bug fixes | 120 | 2 | 200 | 3 | Yes
Music Transitions | 60 | 1 | 120 | 3 | Yes
playtesting | 200 | 11 | 200 | 1 | Yes
documentation | 300 | 3 | 300 | 3 | Yes
Burndown Chart | EST Time | Actual Time | EST Effort | Actual Effort |  | Estimated time taken to complete sprint: | 1640
Starting Values | 1640 | 1580 | 25 | 20 |  | Actual time taken to compelte sprint: | 1580
pause menu | 1580 | 1460 | 21 | 15
story messages narration | 1180 | 1140 | 19 | 12 |  | Estimated effort to complete sprint: | 25
lots of balancing | 680 | 820 | 17 | 10 |  | Actual effort to complete sprint: | 20
UI Bug fixes | 560 | 620 | 15 | 7
Music Transitions | 500 | 500 | 14 | 4
playtesting | 300 | 300 | 3 | 3
documentation | 0 | 0 | 0 | 0
Sprint 4 focused mainly on polish, balancing, story and final improvements to the player experience. I completed the pause menu system and fixed several UI bugs that had been causing issues during gameplay. I also added story narration messages that appear while progressing through the game. This helped improve the narrative aspect of the prototype because earlier feedback suggested that the game lacked a lot of story.
A large amount of time during this sprint was spent balancing gameplay systems. I adjusted the player physics, momentum gain, scoring, multipliers, and procedural terrain values repeatedly because small changes had a major impact on how satisfying the game felt to play. I also implemented music transitions which changed the atmosphere depending on player progress and distance travelled. These transitions helped make the game feel more immersive and supported the increasing tension within the story however they do lag a bit when transitioning not sure why.
Playtesting was another major part of this sprint. Testing helped identify issues with pacing, UI readability, and difficulty scaling. I also completed most of the documentation during this sprint to ensure the project met the requirements. Overall this sprint was more focused on refining and polishing existing systems rather than building new mechanics.